## RecommendationsCompleted
Ticket No | Priority | Complexity | Description | Category | Status
T-5261 | Must-have | ?? | T-5261 Address issue of bloated indexes on tables like user_profilemetadata | Production Issues | Completed
T-5317 | Must-have | Low | T-5317 Tune Data Presence Query – Get information for users who haven’t left the channel - may require un bloating indexes on data_presence | Production Issues | Completed
T-5313 | Must-have | Low | T-4972 Remediate the MultiXacts issue specific parameter changes into CH prod cluster. T-5313 Remove FK constraints from 3 tables | Production Issues | Completed
T-5435 | Must-have | Medium | T-4977 SerializationFailure: Conflict with recovery related related error across all the CH production reader nodes Sub task: T-5435 Optimize query so that it can run faster and does not get cancelled. This may not eliminate all instances of cancellation, but can reduce it. | Production Issues | Completed
T-5073 | Must-have | Low | T-5073 Create new index. get_channel_for_web uses index data_presence_channel_obj_id_5dfdaae0 which is on channel_id and is not very selective. A new partial index on channel_id where is_speaker=true can make query faster. | Quey Optimization | Completed
T-5312 | Must-have | Low | T-5312 Add a new partial index on club_id where is_admin (this will be a very small index) (Data club Member) | Quey Optimization | Completed
T-5318 | Must-have | Low | T-5318 Add index on data_channel - add index on transcription status | Quey Optimization | Completed
T-5316 | Must-have | Medium | T-5316 Add a check to prevent Duplicate key value violates unique constraint "data_userprofiletopic_user_profile_id_topic_id_477bfb15_uniq | Quey Optimization | Waiting for Approval from CH
T-4923 | Must-have | Low | T-4923 Add index: club_active_member_index to model ClubMember (recommendations #1 & #2) - is member = true | Quey Optimization | Completed
T-4950 | Must-have | Low | T-4950 Add index: on data_presence on channel id with condition is_speaker = True | Quey Optimization | Completed
T-4924 | Must-have | Medium | T-4924 Rewrite query: Get members that are pending accept or approval - so it does not use the indexes: is_member, is_pending_approval, is_pending_accept | Quey Optimization | Completed
T-5319 | Must-have | Medium | T-5319 Find and drop Unused Indices | DB Config Optimization | Completed
T-5322 | Nice-to-have | Low | T-5322 Reduce the work_mem parameter | DB Config Optimization | Completed
T-6122 | Must Have |  | Sprint 4 - Query is not able to use the index as function upper is used in predicate on column ‘name’. This prevents existing index to be used. | Model change | Completed
T-5323 | Nice-to-have | Low | T-5323 Reduce idle_in_transaction_session_timeout parameter | DB Config Optimization | Future Recommendation
T-6119 | Must-have |  | Sprint 4 Recommendation - Improving efficiency of Data Activity Table | Design Change | Future Recommendation
T-6120 | Must-have |  | Sprint 4 - 2. Recommendation to make operations on Data_userprofilemetadata more efficient | Design Change | Future Recommendation
T-6121 | Must-have |  | Sprint 4 - Address Lockout/Slow updates on data_channel warnings | Design Change | Future Recommendation
T-6124 | Must Have |  | Sprint 4 - 8. Address Connection Time out warning with data notification | Design Change | Future Recommendation
T-5315 | Must-have | Low | T-5315 Rationalize indexes on data_friends– Remove indexes that are duplicative | Quey Optimization | Future Recommendation

## FutureRecommendations
This is final set of recommendations for improving performance of Aurora Postgres DB and keeping the database healthy. Many of of these recommendation have been discussed before but could not be implemented.. Recommendations will help keeping database lean and healthy to avoid problems in future. CH will be able to scale up the application with increase usage/data volumes without having to making major design changes or migration to other datastores.
Area | Observation | Height Task | Status | DB Objects | Root Cause | Impact | How to address issue
Index Bloating | There are several tables where indexes are bloated. As a result size of the index is much larger than what it should be . Examples - User_profilememetadata where size of the table is 13G, but eeach index is 60G+. With this table uses 300G. Level of bloating is 100X - User Activity - Some indexes are 100G+, while their actual size should be around 70G. Level of bloating is 1.5X | https://clubhouse.height.app/inbox/T-5261 https://clubhouse.height.app/inbox/T-5317 | Tasks completed, but pending production deployement | Postgres: - UserProfileMetadata (time last active, num_followers etc) - Data Presence - Data Activity - Other large tables that have high frequency of updates on indexed columns | 1. Column on which indexes exist are being mutuated (updated) very frequently. Because the way MVCC is implemented in Postgres, this results in lot of redundant rows. Vacuuming is not able to effectively reduce the storage and over a period of time, index start to grow larger in size | This impacts the overall performance of the write and read operations on the table. It can also impact the data replication process where queries may run slower and get cancelled | - Run repack utility to unloat the index. Address the root cause of index bloating - Reduce the frequency of updates on indexed columns
Redundant indexes | Pattern 1: There are tables where there are redundant indexes on Table. If there is index on Col A and another composite index index on Col A + COl B - then first index is not needed as queries with Col A = 'xxx' can use the composite index as long as Col A is leading column in composite index. - Example: User_activity - There is index #1 on User Id and Index #2 on User Id + time-Created. First index can be dropped and all queries on just user_id will be able to use the second index Pattern 2: If there is a unique constraint declared on table, there is no need for another unique index on the table. Unique constraint will provide the functionality of the index and index can be removed - Example: data_userhiddenchannel has unique constraint on table -user_profile_id, channel_id and unique index on same columns the table. Unique index can be removed Pattern 3: Partial index - if where condition is not selective, then partial index does not provide much performance advantage. Partial index can be removed and the Full index will be used w/o any performance degradation - Example : data_friend : Partial index - btree (friend_user_profile_id) WHERE time_unfollowed_at IS NULL. This selects 70% of rows and is not selective. It can be removed. Full index on "friend_user_profile_id" will be as efficient. Pattern 4: Having indexes on boolean column is not effective. Boolean columns store 2 values which is not selective. They should be removed. Instead add a partial index to match the query condition - Example data_clubmembers - index on btree (is_admin), btree (is_pending_accept), btree (is_pending_approval) will not be effective. | https://clubhouse.height.app/inbox/T-5315 | Not discussed. | Few examples have been provided, but all tables need to be reviewed | Redundant Indexes may been created based on the individual query conditions w/o looking overall at how they overlap and if it's helping | This impacts performance of write as more data structures have to be maintained. It can impact the Optimizer getting confused with redundant indexes resulting in a non optimal plan thereby slowing the performance of queries. - My guess is that ~ 20% of indexes are redundant. | Review the list of indexes and wherever you see these patterns, drop the redundant index. Run the queries that involve columns on which index existed, but index was dropped. Ensure the explain plan are optimal. In addition run the Load tests and compare the performance of APIs before and after.
Unused Indexes | Based on latest analysis, there are 37 indexes that are not used on both the reader and the writer nodes. This list has been collected from PG Analyzer | https://clubhouse.height.app/inbox/T-5319 | T-5319 being tested now and ready for deployement by 5/14. It will address 2 indexes on user_profilemetadata Other 35 indexes needs to be reviewed, and decision needs to be made if indexes can be dropped. | auth_user_username_6821ab7c_like authtoken_token_key_10f0b77e_like data_blockeduser_time_created_06a2333e data_channel_agora_url_52677629 data_channel_agora_url_52677629_like data_channel_channel_7fc973c9_like data_channel_time_ended_886afec0 data_club_is_community_80b5ca16 data_clubmember_is_pending_06032810 data_clubmember_time_created_be42bbe0 data_directpayment_is_successful_7391daa9 data_directpayment_payment_intent_id_79252892 data_emailverification_email_684e7e5f data_emailverification_email_684e7e5f_like data_event_is_member_only_91287e90 data_event_visibility_acf8e492 data_historicalincident_agent_id_743e55af data_historicalincident_channel_id_b8771e3b data_historicalincident_reported_id_18813816 data_historicalincident_reported_id_18813816_like data_historicalincident_user_profile_id_b2bd66cc data_ignoredfollowsuggestion_time_created_27831e00 data_invitelink_code_4e8125c7_like data_invitelink_is_active_1246c1aa data_phonewhitelist_phone_number_6a5d0104_like data_reservedusername_username_67ad5638 data_smsverification_phone_number_117ab521_like data_userprofile_phone_number_9baf6ac6_like data_userprofile_suspension_past_counts_a7cbf51e data_userprofile_suspension_source_fc3dfe27 data_userprofile_suspension_source_fc3dfe27 data_userprofile_username_7f714650_like data_userprofilemetadata_num_following_63f9e5a6 data_userprofilemetadata_time_last_active_a1bb1571 data_waitlist_phone_number_192a2faf_like data_waitlist_twitter_verified_1450bb34 user_channel_index |  | This impacts performance of write as more data structures have to be maintained. It increases storage space that is used | Review the list of unused indexes to validate if they are used in queries. Drop the indexes and run load test to verify that the performance of the application has not been impacted.
Archiving old data | There are many large tables that have a temporal nature. The application is interested only in live events/ activity. Once the event/activity is over, data is no longer needed and ready to be archived. - Examples - Data_activity, Data_notification - Only messages that are in future/present are important while the older messages are not important - Data presence - This tables store users who joined a channel and is accessed when the event is on. After event ends, this data is not accessed - Data Channels - Same as data Presence | For data acctivity , following task was logged https://clubhouse.height.app/inbox/T-6119 | This has been deferred as feedback is awaited from Clubhouse. Task logged was for data activity, but there are other tables that are similar and should be considered for partioning and archival | - Data Activity - Data Notification - Data Presence -Data Channel | Functionality for managing older/historical data not part of the architecture | Tables mentioned occupy around 80% of the storage space. Each table has become very large and operations (inserts/updates/queries) will start slowing down. Also the time it takes to extract data and copy to DWH environment will start taking longer. If archiving is implemented, overall size of the database can reduce by 50% or more | - Implement partitioning on the tables. - Create partition per month based on creation_date Example create partition data_channle_052021 ... where creation_date between (05-01-2021 and 05-31-2021) - Drop the partitions for older months after data has been copied to DWH environment.
Locking issues | There are few table like data channel where we see updates waiting to acquire locks. This occurs when same channel record is being updated concurrently from multiple instances of the application OR there is a long running transaction that holds the lock on data channel record for a long time while other updates on same record start coming in parallel. | https://clubhouse.height.app/inbox/T-6121 | This has been deferred as feedback is awaited from Clubhouse. | Data_channel | - Data channel is being updated based on user activity. Since there can be hundreds of users logged in concurrently whose actions in app can results in update to same channel records - this can cause locking. - Or updates to data channel can be part of a long transaction that may be taking longer time to execute and during that period updates to data channel are resulting in locks This requires further research of the application code to understand how records in data channel are being updated and ensure that updates are done in a coordinated manner | This is impacting the performance of the application. Currently majority of the times, application is able to get a lock on data channel after waiting for 2000-3000 msec. In the future as the user base grows, there is a risk that wait time may get longer, or lead to timing out of locks impacting experience of users. Or is worst case, updates will fail leading to data integrity issues. | -Ensure that all updates to data channels are done in a coordinated manner. Queues can be implemented to add messages for updates to data channel from user sessions . USe a common background process to read messages and update the data channel. Multiple message can be aggregated to reduce the frequency of updates on data channel. -Review the application code to find if there is any update to channel as part of long running transaction. If possible decouple it or ensure there is a commit performed in shorter intervals to release the locks.
Use Sequences to create Ids | There are few tables like User profile, channels etc where we see Primary Key Ids being generated by calling functions to generate random numbers | No Task logged | Not discussed | User profile data channel data club data club members |  | Multiple issues with this approach a) Ids are not serial and continuous b) There is an overhead of using function as it has to check if generated id is not already being used c) Also this is not consistent with best practices and approach being used in other tables like data_activity etc | Change the id creation mechanism to use sequences. Ensure that starting if dor Seq is max of existing Ids in table to avoid conflict
Use of FK constraints | - Club House has implemented Foreign Key constraints on tables. FKs constraints have been declared on columns that reference PK of parent table. FKS are used to maintain referential integrity checks. - If referential integrity checks have been implemented in the app, it's not necessary to implement at the DB level. - Enforcing referential integrity at DB level absolutely impacts insert and delete write performance, because a lookup (read) is required for both. Update write performance is only impacted if it changes the key. Read only performance is not impacted. - FK also results in generating Multixacts that are stored in memory, but if no of FK access becomes large, it starts spilling over to disk. Long term resolution of this issue this is reducing FKs. | https://clubhouse.height.app/inbox/T-5313 | T-5313 is ready for deployement. It will address 5 FK constraints on 3 tables - userprofilemetadata,data_Club and data_useraffinity. CH should review remaining FK constraints and decide if they should be retained or not. | There are around 200+ FKs implemented across 60 tables in CH schema. All tables that contain a column that references PK of parent table, has FK constraint declared |  | It slows down performance of updates and inserts. It may also result in Multixact issues where data starts spilling over to disk | Drop FKs on tables. Ensure that data integrity check in being performed in application code. It may be safe to drop the FK constraints - as we don't see any FK violations in DB logs. This implies that application code enforces the FK check, and data that is inserted is valid data.
Rationalizing Inserts/Updates on Writer nodes | There are many tables where the volumes of inserts and updates can be reduced w/o compromising the functionality of the app. For example when Room starts, message is generated for every member associated with the club to alert them about the event. It results in 1000s of messages being inserted in data_activity resulting in 100M records added daily. When a user is active in a room/channel, time last active is updated in user profile metadata very frequently. It results in 60K updates per min on this table. Many of these updates can be reduced. Frequency of updates on Auth Token table is very high at rate of 300K/min When a room is live, data channel record is updated frequently to keep track of user activity and calculate aggregate metrics like no of followers/followed etc | https://clubhouse.height.app/inbox/T-56119 https://clubhouse.height.app/inbox/T-6120 | This has been deferred as feedback is awaited from Clubhouse. | data_acivity data_userprofilemetadata data_channel |  | High frequency updates/inserts are creating excessive traffic on the writer node and can result result in bottlenecks impacting the performance/responsiveness of the system. It may already be causing locking of records and issues with replication | - Data Activity : Redesign to not insert messages for every member when a channel starts. Can this be deferred and messages are generated when a user signs in and navigates to the notifications tab. - User profile metadata - Info related to keep track of users last time active and other metrics is frequently updated in the table. Can this be refactored to store frequently changing information in cache or some other data structure. Information is persisted at reduced frequency in postgres table and rest of the times needed information is pulled out of cache or other data structures. - Data Channel - Frequency of update to this table should be reduced and only done at important critical points during the life cycle of channel - when a room starts, or when it ends. Channel updates related to user activity should be maintained in table like data presence or in some caching structure. Explore use of queues to keep log of all events for channel. Updates can be aggregated and persisted in Postgres table at reduced frequency and coordinated from a single process vs multiple processes updating same records concurrently.
Segment Workloads to execute on specififc reader nodes | Currently the workloads are segmeneted by writes Vs read operations. All writes are executed on Writer Node while queries are spread round robbin on multiple reader nodes. There is no segementation to direct certain types of queries to specific reader node. Certain workloads (like batch processing, social graph OLTP queries ) can execute more efficently if they can be directed to run on dedicated nodes and not have to contends with other workloads. | No task logged | Not discussed |  |  |  | Can reader nodes be reserved to execute only - Example can data intensive batch jobs be directed to execute on a specific reader node and not run on nodes that execute OLTP queries - Can social graph OLTP queries that are I/O intense be executed on a specifc node so that as much data for query is available from DB cache w/o need to perform I/O from disk that is more expensive operation.
Improving performance of Social graph queries | There are few queries on data friends that are slow. Query 1 is to find friends who follow each other mutually. A follows B and B follows A. This query is expensive (almost 80% of the overall cost) as it requires multiple level of traversals and joins and uses multiple indexes. Query 2 to find friends that match two lists a) Given list of followers b) Given list of followed. This uses 2 indexes which slow the query | No task logged as CH advised they are moving all social grpah operations to Dynamod DB | Not discussed |  |  |  | Query 1: Rewrite the subquery on data_friends to execute more efficiently as shown above Use CAST function to stop the Optimzier from using one of the indexes that is making data query slower. Query 2: - Rewrite the query to drive the queries from the results from one index on friend_user_profile that has a small list rather than index on user_profile_id - To turn off the index on user_profile_id , apply the CAST function as shown above. - Conditionally add the CAST clause when the list of ids for friend_user_profile is smaller compared to list for user_profile_id
Replicate data from Aurora to GCP using the S3 Export utility | Club House clones prod DB multiple time a day to create a copy of Database. Stitch IO ETLS run to extract the data and load the data to GCP for supporting analytics |  |  | All Objects |  | Cloning DB and frequently running ETL to extract and load data is effort intensive and can result in delays of data being available for analysis | An alternative approah can be used to reduce the overhead and mkae process efficent, reduce delays. - Use Aurora Export DB Snapshot to S3. This will export data from prod tables as parquet files in compressed format to S3. - The S3 export process runs in the background and doesn't affect the performance of your active DB cluster. - After data has been exported, files can be accessed directly from GCP w/o having to run Sticth IO to extract and load the data - AWS native tools like g Athena or Redshift Spectrum can be used to perform the analysis

## Images (hidden)
Test | 1. When this scale to billions of users, this table will perhaps need to scale out(Shard). Embedding all data in User Object will let you scale seamlessly without worrying about colocating data from child and parent tables. Choose user profile id as you shard key(High cardinality). Make sure it is randomized before being written into the DB. 2. If people with millions of followers get blocked by several users, this screen will be slow for them.